## Start Here
4Prep — 3-Week MVP Plan
Goal: a PUBLIC MVP live at app.4prep.ai — browse real sourced universities, a Φ v0.1 fit score, and a Perplexity-powered chat counselor.
Window: Mon Jul 27 → Sun Aug 16, 2026 (3 weeks) · Capacity: ~20 hrs/week · Supersedes the 12-week plan
THE HOUR BUDGET
3 weeks × 20 hrs × 0.7 slack | 42 real hours — the hard ceiling. This plan spends exactly 42 (3 × 14).
The honest read | 42 hrs ≈ one full-time week. A FULLY PUBLIC launch in that time is aggressive: auth, privacy policy and RLS are non-optional overhead. Scope is cut to the bone — 10 universities, 1 chat counselor, no admin tooling. If something slips, cut universities (5 not 10) and the other 4 AI tools — never auth, privacy, or the grounding guardrails.
Head start | The 7-screen UI, trust primitives and DataPoint contract are already built and good. This plan puts a real spine into a real skin.
KEY DECISIONS (Jul 27)
AI counselor | Perplexity API powers a CHAT counselor (reverses the earlier structured-only call). Perplexity is WEB-grounded, not database-grounded — so it must be constrained: pass verified DB records in as context, answer factual questions (tuition/deadline/IELTS/scholarship) ONLY from those, show citations, and refuse honestly rather than guess. General advice may use web sources but must be visibly separate from sourced figures.
Fit score | Φ v0.1 = a simple deterministic weighted sum over the five existing components (academic, financial, language, career, geographic). NOT Perplexity-generated. This keeps the public EPIF claim (paper, articles, EB-1A) true. Calibrate against the paper's exact equations later.
Audience | Fully public at app.4prep.ai — therefore auth, privacy policy and RLS hardening are in scope in Week 3.
BUY, DON'T BUILD | Auth → Supabase Auth · DB/storage/backups → Supabase · Hosting → Vercel · AI → Perplexity API · Errors → Sentry free tier.
CUT LIST (not building) | The other 4 AI tools as real engines (leave on sample or hide) · desktop/Niche redesign · admin console & verification queue · Outcome Ledger + Φ calibration · 300-university target (10 instead) · CI grounding-eval harness (manual spot-check instead) · M2/M5/M6 polish → backlog.
THE RISKS | (1) Perplexity answering university facts from the web instead of your DB = the exact fabrication risk your brief names. The constraint in Week 2 is what prevents it. (2) Public launch means real students' grades and budgets — the privacy policy in Week 3 is not optional. (3) 10 universities means many students hit a coverage gap; the honest empty state matters more than usual.
STATUS — 28 JUL | Week 1 DONE. Week 2 DONE (counselor code-complete but not live). Week 3 IN PROGRESS — auth, privacy page and RLS are built and anon-tested. Build passes, 14/14 tests pass. Catalogue switched to 10 US universities (Harvard/Yale/Princeton need-blind · Berea · Illinois Wesleyan/Clark · Southern Miss/Alabama/Nebraska Kearney · Houston City College 2+2). Roughly 2 weeks ahead of schedule on build; the bottleneck is now provisioning, not code.

## Task Plan
Week | Week goal | Task | Est. hrs | Due | Status | Notes
W1 | Foundation: database + real data + Φ v0.1 | Git hygiene: add .gitignore; delete dead files (app/dist, src/__smoke.tsx, root package-lock.json, .DS_Store, .smoke-out) | 1 | 2026-07-27 | Done | Done 27 Jul — .gitignore + dead files removed
W1 | Foundation: database + real data + Φ v0.1 | Stand up Supabase; build schema from types/index.ts — non-null source FK on every fact field + RLS policies | 5 | 2026-07-29 | Done | Live on Supabase Cloud (Tokyo); 6 forward-only migrations
W1 | Foundation: database + real data + Φ v0.1 | Seed 10 REAL US universities with sourced figures (tuition, fees, room+board, aid, deadlines, tests) | 5 | 2026-07-31 | Done | SWITCHED TO US: 10 US unis, 50 verified sources, 145 sourced facts / 25 honest unknowns
W1 | Foundation: database + real data + Φ v0.1 | Φ v0.1: deterministic weighted 5-component fit score + unit tests; document the weights | 3 | 2026-08-02 | Done | Now Φ v0.2 — recalibrated for US net-cost-after-aid; 10 unit tests
W2 | Wire it up + the Perplexity counselor | Data layer (client, repository, mappers, DataProvider); all 7 screens read Supabase instead of mock data | 6 | 2026-08-05 | Done | src/mock deleted; all screens on live Supabase; S1 fixed
W2 | Wire it up + the Perplexity counselor | Fix S2 (contradictory fit display) + S3 (budget vs scholarship filter semantics) + M1 (em-dash) | 2 | 2026-08-06 | Done | S2, S3, M1 fixed + 3 extra UI bugs fixed 28 Jul
W2 | Wire it up + the Perplexity counselor | Perplexity chat counselor: API wiring, DB records passed as context, citations shown, honest refusal when unsourced | 6 | 2026-08-09 | In progress | CODE COMPLETE incl. validator + strike audit. Blocked: needs PPLX key + function deploy
W3 | Harden, deploy, LAUNCH public | Supabase Auth (email) + persist profile & saved plans per user + real routing/URLs | 4 | 2026-08-11 | Done | Auth, owner-only RLS, real URL routing all built
W3 | Harden, deploy, LAUNCH public | Privacy policy + consent copy + RLS hardening review (profiles hold grades & budget) | 3 | 2026-08-12 | In progress | Page + RLS done & anon-tested. Pending: privacy contact, deletion process, backups
W3 | Harden, deploy, LAUNCH public | Deploy: Vercel + Supabase prod + app.4prep.ai DNS + secrets/env; backups on | 3 | 2026-08-13 | Not started | Deferred by Jeff — running locally until just before launch
W3 | Harden, deploy, LAUNCH public | Mobile QA on real phones + grounding spot-check on 10 profiles + fix top bugs → LAUNCH | 4 | 2026-08-15 | Not started | Final gate. Red-team the counselor once it is live
|  | TOTAL | 42 | hours / 42 budget

## Week Summary
Week | Dates | Goal | Deliverable | Definition of done | Hrs | Status
W1 | Jul 27 – Aug 2 | Foundation: database + real data + Φ v0.1 | Live Supabase schema, 10 real sourced universities, tested Φ v0.1 | A profile scores against real DB rows in a unit test; 10 universities exist with a source on every figure | 14 | Done
W2 | Aug 3 – Aug 9 | Wire it up + the Perplexity counselor | All 7 screens on real data; chat counselor answering from DB records with citations | Changing intake answers changes the ranked list; the counselor refuses (not guesses) when a figure isn't in the DB | 14 | Done
W3 | Aug 10 – Aug 16 | Harden, deploy, LAUNCH public | Public MVP live at app.4prep.ai with auth + privacy policy | Auth + privacy + RLS built and tested. Remaining: counselor go-live, backups, privacy contact, deploy, mobile QA. | 14 | In progress

## QA Audit
ID | Severity | Issue | File : line | Fix in | Status
S1 | Serious | Results ignore intake answers — always attaches samplePathway | Intake.tsx:105 | Week 2 | Done
S2 | Serious | Fit score shown with no profile AND a contradictory 'needs your profile' message | UniversityProfile.tsx:132/274/288 | Week 2 | Done
S3 | Serious | Budget filter excludes scholarships; top pick vanishes under its own ceiling | Search.tsx:51–64 | Week 2 | Done
M1 | Minor | Em-dash used for missing data — violates the product's own rule | UniversityProfile.tsx:140; Saved.tsx:99 | Week 2 | Done
M2 | Minor | Compare & Saved ignore devState (loading/error/offline undesigned) | Compare.tsx; Saved.tsx | Backlog | Done
M3 | Minor | Duplicate saves append the same plan twice | Results.tsx:186 | Week 3 | Done
M4 | Minor | Repo hygiene: dead files + missing .gitignore | root; app/ | Week 1 | Done
M5 | Minor | fmtMoney only symbolizes USD/EUR though type allows HUF/KRW/TRY/KZT/UZS | primitives.tsx | Backlog | Not started
M6 | Minor | No linter / test runner beyond the SSR smoke test | app/ | Week 1 | Done
R1 | Risk | Conflicting stack stories (Lovable vs Next.js vs Vite) | project-wide | Week 1 | Done
R3 | Risk | No source control | repo | Week 1 | Done
R4 | Risk | In-memory routing — no URLs/persistence; blocks auth & deep links | state.tsx | Week 3 | Done
R5 | Risk | No Φ engine — fit numbers hand-authored. Now scoped as Φ v0.1 | mock/sample-data.ts | Week 1 | Done
R6 | Risk | NEW: Perplexity is web-grounded, not DB-grounded — can answer university facts from random pages | chat counselor | Week 2 | In progress
H1 | Housekeeping | Remove app/.smoke-out/ left from the audit | app/.smoke-out/ | Week 1 | Not started