## Start Here
4Prep — 3-Month Plan
Goal that matters: a public soft launch at app.4prep.ai — accounts + a first cohort of real users, on real sourced data.
Window: Mon Jul 27 → Sun Oct 18, 2026 (12 weeks) · Capacity: ~20 hrs/week
THE HOUR BUDGET
12 weeks × 20 hrs × 0.7 slack | 168 real hours — the hard ceiling. The plan spends exactly 168.
The honest read | 168 hrs ≈ 4 full-time weeks over 3 months, solo. The full vision (300 unis, 5 AI systems, calibration, admin console) does NOT fit. 'Soft launch' here = 1 AI flow, ~15–20 sourced unis, real accounts, deployed, small real cohort. Narrow + real beats broad + fake.
Head start | The front-end (7-screen UI, trust primitives, DataPoint contract) is done and good. You're putting a real spine into a real skin.
HOW TO USE THIS WORKBOOK
Weekly Plan tab | Every task, with its own due date and Est. hrs. Set Status from the dropdown; Done rows turn green. Use the filter to view one week or one month.
Week Summary tab | The 12-week overview: goal, deliverable, definition of done, hours, dependencies. Total hours auto-sums to 168.
QA Audit tab | The Stage-1 review issues (S1–S3, M1–M6, R1–R5) with file:line, the week each is fixed in, and a Status dropdown.
Put it in Drive | Drag this .xlsx into Google Drive (it opens as a Google Sheet), or connect Drive and I'll upload it for you.
BUY, DON'T BUILD | Auth → Supabase Auth · Hosting/DB/storage/backups → Supabase + Vercel · Error monitoring → Sentry · Data-entry labor → hire a 4Prep alum · Source snapshots → save manually for ~20 unis.
TECH DEBT TO ACCEPT | Simplified Φ normalization (versioned, self-signed) · manual golden-set grounding check but KEEP the runtime validator · 1 of 5 AI tools · ~15–20 unis not 300 · mobile-first, desktop passable · Supabase Studio / sheet-import instead of an admin console.
CUT LIST | The other 4 AI tools · the full Ground Truth admin console · Outcome Ledger + Φ calibration · the 300-university target · the Niche desktop redesign · multi-language · automated source monitoring / correction loop / partner API.
THE RISK | Fits only if weeks 1–3 hold. If Φ is hard or the paper is ambiguous (R5), weeks 2–3 slip and eat the buffer — which is why they're front-loaded. If you slip, cut universities (10 not 20), NEVER the safeguards.
AI COUNSELOR | Structured only — NO chatbot (decided 2026-07-24). The counselor speaks through the Pathway Generator + the 5 tools as sourced cards, kept honest by the claim validator + designed refusal states. Built in Week 6 (real Claude output replaces the hardcoded text in the existing AIResponseBlock cards) and hardened in Week 8 (golden-set grounding check). Deliberately no chat window — nothing invites a question you have no sourced answer for.

## Weekly Plan
Week | Month | Week goal | Task | Est. hrs | Due | Status | Notes
W1 | Month 1 | Decide the stack & lay the real foundation | Lock canonical stack in writing: Vite/React front-end + Supabase backend; retire the Lovable/Next.js ambiguity | 2 | 2026-07-27 | Done | Dependency-critical (R1)
W1 | Month 1 | Decide the stack & lay the real foundation | git init + GitHub remote + .gitignore; delete dead files (dist/, __smoke.tsx, root lockfile, .DS_Store) | 1 | 2026-07-27 | Done | Fixes M4, R3 · 21 commits, origin/main live
W1 | Month 1 | Decide the stack & lay the real foundation | Stand up Supabase; build schema from types/index.ts with a non-null source FK on every fact field | 5 | 2026-07-30 | Done | 16 migrations applied
W1 | Month 1 | Decide the stack & lay the real foundation | Extract EPIF Φ equations from the paper into an implementation spec; log ambiguities | 3 | 2026-07-31 | Done | scoring/phi.ts — versioned, unit-tested
W1 | Month 1 | Decide the stack & lay the real foundation | Source ONE real university end-to-end and time it = your throughput baseline | 3 | 2026-08-02 | Done | 10 unis, 50 verified sources
W2 | Month 1 | A real, tested scoring engine + read contract | Implement Φ as a deterministic, versioned function; unit-test against the paper's worked examples | 6 | 2026-08-05 | Done | Deterministic + versioned
W2 | Month 1 | A real, tested scoring engine + read contract | Resolve any underspecified normalization with founder; version the decision (don't improvise) | 2 | 2026-08-06 | Done
W2 | Month 1 | A real, tested scoring engine + read contract | Define the minimal Gateway query: profile → candidate records + citation IDs | 4 | 2026-08-08 | Done | data/repository.ts is the only Supabase caller
W2 | Month 1 | A real, tested scoring engine + read contract | Privacy/legal self-check: republishing sourced figures + storing student profiles (RLS) | 2 | 2026-08-09 | Done | /privacy route live
W3 | Month 1 | Wire the UI to real data | Swap sample-data.ts reads for Supabase queries behind the same DataPoint contract | 6 | 2026-08-12 | Done
W3 | Month 1 | Wire the UI to real data | Make intake actually drive candidate selection + Φ ranking | 5 | 2026-08-14 | Done | Fixes S1
W3 | Month 1 | Wire the UI to real data | Fix S2 (contradictory fit display) + S3 (budget vs scholarship semantics) | 2 | 2026-08-15 | Done | Fixes S2, S3
W3 | Month 1 | Wire the UI to real data | Keep the ribbon + DataValue/MissingValue enforcement intact | 1 | 2026-08-16 | Done
W4 | Month 1 | Start the data fill + bring in help | Shortlist the ~15–20 universities that matter (demand-first, with founder) | 2 | 2026-08-17 | In progress | Catalogue is at 10 of the 15–20 target
W4 | Month 1 | Start the data fill + bring in help | Build the dead-simple entry path: Sheet→CSV import or 1-screen form (NO admin console) | 4 | 2026-08-19 | In progress | Template xlsx exists; no import path in admin yet
W4 | Month 1 | Start the data fill + bring in help | Enter + source 6–8 universities yourself, refining the process | 6 | 2026-08-22 | Done | 10 entered and sourced
W4 | Month 1 | Start the data fill + bring in help | Brief a 4Prep alum to source records to your standard | 2 | 2026-08-23 | Done | Brief written (4Prep_Data-Researcher-Brief.pdf); hire not confirmed
W5 | Month 2 | Complete the depth-first dataset | Reach ~15–20 universities total (you + helper) | 8 | 2026-08-28 | Not started | Blocked on 15 — still 10 universities
W5 | Month 2 | Complete the depth-first dataset | Enter the cohort's relevant scholarships, sourced | 4 | 2026-08-29 | In progress | scholarships + university_scholarships tables exist; coverage unverified
W5 | Month 2 | Complete the depth-first dataset | Spot-audit 10% of records against their sources | 2 | 2026-08-30 | Not started
W6 | Month 2 | The AI counselor — grounded, structured (no chatbot) | AI counselor: write the prompt + wire the Claude API (profile + record bundle + Φ + citation IDs → structured JSON pathway) and render it into the existing AIResponseBlock cards (Results + Pathway Generator). No free-text facts. | 8 | 2026-09-03 | Done | CORE · counselor edge fn, Perplexity, structured cards, no chat window
W6 | Month 2 | The AI counselor — grounded, structured (no chatbot) | Build the claim validator: strip any figure/name/deadline with no citation ID; on a missing required fact, return an honest refusal instead of a guess. | 6 | 2026-09-06 | Done | validateFigures + semanticFields + strike log
W7 | Month 2 | Accounts + saved plans | Supabase Auth (email) | 3 | 2026-09-08 | Done | BUY, don't build · email + Google + reset + delete
W7 | Month 2 | Accounts + saved plans | Persist profiles + saved pathways per user; wire the Saved screen to real storage | 7 | 2026-09-11 | Done
W7 | Month 2 | Accounts + saved plans | Replace in-memory routing with real routes/URLs so login + deep links work | 4 | 2026-09-13 | Done | Fixes R4 · routes.ts + AppLink + vercel rewrites
W8 | Month 2 | Honesty + grounding pass | Golden set of ~10 realistic profiles; verify every claim maps to a record and missing → refusal | 5 | 2026-09-16 | Not started | src/qa/ is empty
W8 | Month 2 | Honesty + grounding pass | Tune refusal/caveat behavior; flip verified records off 'sample'; keep the ribbon accurate | 4 | 2026-09-18 | In progress | Refusals tuned (F-02/F-04); verified_universities view still unused
W8 | Month 2 | Honesty + grounding pass | Fix M1–M3 (em-dash for missing data, devState on Compare/Saved, duplicate saves) | 3 | 2026-09-19 | Done | Fixes M1, M2, M3
W8 | Month 2 | Honesty + grounding pass | Wire Sentry | 2 | 2026-09-20 | Not started | BUY · no Sentry in either package.json
W9 | Month 3 | Deploy to the real domain | Deploy front-end (Vercel) + Supabase prod; wire app.4prep.ai DNS | 5 | 2026-09-23 | Not started | app.4prep.ai does not resolve. Marketing site at 4prep.ai is a separate deploy
W9 | Month 3 | Deploy to the real domain | Production RLS check: the app reads only verified rows; profiles are private | 3 | 2026-09-24 | In progress | RLS on all 25 tables, 38 policies; no live two-account test
W9 | Month 3 | Deploy to the real domain | Enable backups; run one restore drill | 2 | 2026-09-25 | In progress | Backup seen 4 Aug; no restore drill, no PITR
W9 | Month 3 | Deploy to the real domain | Responsive-desktop pass — NOT the Niche redesign, just not-broken on a laptop | 4 | 2026-09-27 | In progress | UI modernised 7 Aug; 588 kB main chunk still unaddressed
W10 | Month 3 | Pre-launch hardening | Privacy policy + consent copy BEFORE any real user | 3 | 2026-09-29 | In progress | Screen exists; needs analytics + lead-capture copy
W10 | Month 3 | Pre-launch hardening | Mobile QA on real phones; fix the top issues | 4 | 2026-10-01 | Not started
W10 | Month 3 | Pre-launch hardening | Evidence pack: dated screenshots, what's live, feature demos (brief deliverable + EB-1A evidence) | 4 | 2026-10-03 | In progress | Two audits + 12 docs exist
W10 | Month 3 | Pre-launch hardening | Founder sign-off that nothing on screen diverges from the paper/public narrative | 3 | 2026-10-04 | Not started
W11 | Month 3 | Soft launch to the cohort | Invite a small first cohort (existing 4Prep leads/students) | 2 | 2026-10-05 | Not started
W11 | Month 3 | Soft launch to the cohort | Instrument: pathway runs, refusal rate, saves, citation clicks, coverage-gap misses | 5 | 2026-10-07 | Not started
W11 | Month 3 | Soft launch to the cohort | Support the cohort live; log every bug + data gap | 5 | 2026-10-10 | Not started
W11 | Month 3 | Soft launch to the cohort | Daily triage | 2 | 2026-10-11 | Not started | It will feel premature — launch anyway
W12 | Month 3 | Stabilize & ship the record (LAUNCH) | Fix the top launch bugs; fill the specific gaps that blocked real users | 7 | 2026-10-15 | Not started
W12 | Month 3 | Stabilize & ship the record (LAUNCH) | Finalize the documentation/evidence pack with real user counts + screenshots | 4 | 2026-10-17 | Not started
W12 | Month 3 | Stabilize & ship the record (LAUNCH) | Write the public description that matches exactly what shipped | 3 | 2026-10-18 | Not started
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Rewrite the 4prep.ai landing claims: drop 92%/81%/67% fit, 'Risk level', 'on track'; swap Germany/NL + DAAD for the real US catalogue; replace 'trained on real advising' with the sourced-and-refuses claim | 1.5 | 2026-08-11 | Not started | BLOCKER · the live site contradicts the DataPoint honesty contract
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Point app/.env and admin/.env back at the QA project (forrvcsttklmpmfhxums) | 0.25 | 2026-08-11 | Not started | SUPERSEDED — target is the 4PrepAi production project, not QA (decided 10 Aug)
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Migration: leads table — RLS on, zero policies (service-role only), user_id ON DELETE SET NULL | 0.75 | 2026-08-11 | Done | Written, not applied. Needs one run against a real Postgres before Production
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Build AskACounselor: name + contact + prefilled context line; idle/submitting/submitted/failed, no silent failure | 1 | 2026-08-12 | Done | 7 states + honeypot; 8 tests passing
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Wire the handoff onto the pathway results screen (source='results') | 0.5 | 2026-08-12 | Done | Below the five Φ components, after the sourced answer
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Wire the handoff into MissingValue in Trust.tsx (source='gap') | 0.5 | 2026-08-12 | Done | On HonestGapCluster — one offer per cluster, institution gaps only
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Surface leads in the admin console list view | 0.25 | 2026-08-12 | Done | admin-api lead_inbox/claim/resolve + audit; console tab shows oldest wait
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | PostHog EU init behind VITE_POSTHOG_KEY: identified_only, replay disabled, mask_all_text | 0.5 | 2026-08-13 | Not started | BUY · missing key must be a no-op, not a crash
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Instrument exactly nine funnel events (intake→pathway→save→counselor→lead) | 1 | 2026-08-13 | In progress | 4 of 9 in place behind src/data/analytics.ts shim; no provider wired
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Add analytics + lead-capture disclosure to the privacy policy screen | 0.25 | 2026-08-13 | In progress | Lead-capture section written; analytics disclosure still owed until PostHog lands
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Add /support to app/vercel.json rewrites | 0.1 | 2026-08-14 | Not started | Catch-all covers it, but the list reads as exhaustive
W3 | Month 1 | Startup gap: honest front door, handoff, measurement (added 10 Aug) | Seed program_facts for the other three subjects, OR cut intake to the subjects you can source | 1 | 2026-08-14 | Not started | Intake offers 4 subjects; only Computer Science has coverage
|  |  | TOTAL |  | hours across 56 tasks. Original budget 168 across 44; the 10 Aug additions are new scope, so the ceiling is now the thing to defend.

## Week Summary
Week | Dates | Month | Goal | Deliverable | Definition of done | Est. hrs | Status | Depends on
W1 | Jul 27 – Aug 2 | Month 1 | Decide the stack & lay the real foundation | Repo + live Supabase schema + 1 real sourced university + Φ spec | Schema deploys, one real record exists, minutes-per-university known | 14 | Not started | —
W2 | Aug 3 – Aug 9 | Month 1 | A real, tested scoring engine + read contract | Φ passing paper unit tests + a documented query function | npm test green on Φ; a profile returns real candidates from Supabase | 14 | Not started | W1
W3 | Aug 10 – Aug 16 | Month 1 | Wire the UI to real data | App ranks real universities from real data for an entered profile | Change intake answers → ranked list and fit change; every number sourced | 14 | Not started | W2
W4 | Aug 17 – Aug 23 | Month 1 | Start the data fill + bring in help | ~8 verified universities live | 8 render with sourced figures, zero invented values | 14 | Not started | W3
W5 | Aug 24 – Aug 30 | Month 2 | Complete the depth-first dataset | ~15–20 universities + scholarships, sourced | Coverage spans cohort targets; audit clears accuracy bar | 14 | Not started | W4
W6 | Aug 31 – Sep 6 | Month 2 | The AI counselor — grounded, structured cards (no chatbot) | One real profile → a grounded, sourced pathway written by Claude into the existing cards | A deliberately missing figure is provably stripped by the validator (red-team once); no chat window exists | 14 | Not started | W3, W5
W7 | Sep 7 – Sep 13 | Month 2 | Accounts + saved plans | Sign up → run → save → log out → return → still there | The brief's Phase-3 gate passes for a real account | 14 | Not started | W6
W8 | Sep 14 – Sep 20 | Month 2 | Honesty + grounding pass | Passing manual grounding check + clean states | 10/10 golden profiles behave; zero uncited figures on screen | 14 | Not started | W7
W9 | Sep 21 – Sep 27 | Month 3 | Deploy to the real domain | Live at app.4prep.ai on real data | End-to-end use on the real domain from a fresh device | 14 | Not started | W8
W10 | Sep 28 – Oct 4 | Month 3 | Pre-launch hardening | Launch-ready app + live privacy policy + evidence pack v1 | You sign off; policy is live | 14 | Not started | W9
W11 | Oct 5 – Oct 11 | Month 3 | Soft launch to the cohort | Real users generating real pathways | A few real users completed + saved a pathway; usage data + gap list in hand | 14 | Not started | W10
W12 | Oct 12 – Oct 18 | Month 3 | Stabilize & ship the record | Stable public soft launch + a provable evidence pack | Live, real users have used it, every public claim maps to a working feature | 14 | Not started | W11
[5 empty] | TOTAL | 168

## QA Audit
ID | Severity | Issue | File : line | Fix in | Est. hrs | Status
S1 | Serious | Results ignore intake answers — always attaches samplePathway; any off-sample profile gets the canned result | Intake.tsx:105 | Week 3 | ~2 | Not started
S2 | Serious | Shows a fit score with no profile AND a contradictory 'needs your profile' message; sample vs real profile on one screen | UniversityProfile.tsx:132/274/288 | Week 3 | 1–2 | Not started
S3 | Serious | Budget filter excludes scholarships; the #1 pick (Danubia $11,300) vanishes at an $8,000 ceiling | Search.tsx:51–64 | Week 3 | 2–3 | Not started
M1 | Minor | Em-dash for missing data — violates the product's own rule | UniversityProfile.tsx:140; Saved.tsx:99 | Week 8 | 0.25 | Not started
M2 | Minor | Compare & Saved ignore devState (loading/error/offline undesigned) | Compare.tsx; Saved.tsx | Week 8 | 1 | Not started
M3 | Minor | Duplicate saves append the same plan twice | Results.tsx:186 | Week 8 | 0.5 | Not started
M4 | Minor | Repo hygiene: delete dead files (dist/, __smoke.tsx, root lockfile, .DS_Store); add .gitignore | root; app/ | Week 1 | 0.5 | Not started
M5 | Minor | fmtMoney only symbolizes USD/EUR though the type allows HUF/KRW/TRY/KZT/UZS | primitives.tsx (fmtMoney) | Backlog | 0.5 | Not started
M6 | Minor | No linter / test runner beyond the SSR smoke test | app/ | Backlog | 1 | Not started
R1 | Risk | Three conflicting stack stories: Lovable (brief) vs Next.js (proposal) vs Vite (code) | project-wide | Week 1 | — | In progress
R2 | Risk | Desktop redesign not started — building depth on the mobile shell then redesigning = rework | codex-design-prompt.md | Cut | — | Not started
R3 | Risk | No source control — there is no .git in the repo at all | repo | Week 1 | — | Done
R4 | Risk | In-memory routing — no URLs/persistence; reworks when accounts/deep links land | state.tsx | Week 7 | — | Not started
R5 | Risk | No Φ engine exists — fit numbers are hand-authored, not computed from EPIF | mock/sample-data.ts | Week 2 | — | Not started
H1 | Housekeeping | Remove app/.smoke-out/ — a build folder left from the audit (sandbox couldn't delete it) | app/.smoke-out/ | Week 1 | — | Not started